## Sprint Content
General Prerequisites :
Set up connexion FSM / SAP
Service order types, service notice types, PM activity types, priorities defined & validated
Maintenance strategies defined & validated
Sample master data loaded (FR, GR, BE)
Define a Wind Turbine Checklist with conditions for installation (PV excluded)
Sprint content | Prerequisites | Detail | Deliverable | Sprint demo | KUT population | Actions following sprint review | Actions Nagarro | Remarks
Sprint 1
Management of Assets | Business and IT has defined the final Asset structure for Wind turbine and Solar Panels Data loaded in SAP QS4 including : FL/Equipment / Classes / Characteristics | Identification process Characteristic change history Master Data Configuration and replication to FSM Asset Documentation replication to FSM | Proaxia Interface Customizing PM and FSM Customizing Development Specifications | One Example of Wind Turbine Structure to be presented to the Business including FSM view. Process of new Creation of Farm by copy Process of characteristic identification (FSM Flow) | Method/ Area Manager | Preparation of Migration Template for all Assets | Writing of development specifications | Some actions will need to be performed manually due to time constraints and the development delivery schedule: The Service Order will be triggered manually. Manual actions will be carried out to simulate the automatic processes that will be implemented by a specific development to be delivered in the future.
Maintenance of Maintenance Plans | Business has prepared the checklist with conditions Class and Characteristics have been created for Assets including all required information (components / Subcontracting,documentation...). | Configuration of one checklist template (Wind turbine identification) Configuration of one maintenance plan (Wind turbine installation) E2E process for a wind turbine with maintenance plan & task list with components |  | •Presentation of all objects involved in the Preventive maintenance Preparation including •One maintenance plan for wind turbine installation •One core checklist template for Wind turbine installation •Service orders generation (manual call) •Demo of Preventive Maintenance assignment and Execution •Training session on check list template creation and roll out by EDFRE (Wind turbine and PV) | Method/Area Manager | Creation of checklists for all maintenance types and all countries (responsability : Method FR, GR, BE) Roll out for PV will be done by EDFRE
Sprint 2
Management of Service Notice | Service Notice Types with Codes defined Service Notice Attributes defined : •Priority •PM Activity Type Rejection Cause Catalog Defined List of Alarm defined | Corrective, Feedback (NOK) | service notices and PM activity types customized Replication of Service Notice to FSM customized Smartform for service notice creation from FSM with standard fields | Process creation of Service Notice From SAP Process creation of Service Notice from FSM with standard fields | Area Manager |  | -Writing of development specifications Delivery of custom developments Automatic creation of smarforms following NOK tasks | Regarding Service Notice creation from FSM : Some of the requested features require specific developments to be demonstrated. These developments will not be ready during this Sprint. Therefore, we will only present the replication using standard fields, and the demonstration will be completed once the developments are finalized.
Management of Service Order | Service Order Types with Codes defined Service Order Attributes defined : •Priority •PM Activity Type Mapping table between Service Notice type and Service Order type. Missing Time Activity Types to be defined created and Valuated Unproductive hours and Absence Types to be defined | Service Order Attributes and Categorization Dispatching board for Area Manager Absence Types | service order types customized Planner Group Customized User Status customized Service Order replication customizing worflow steps customized activity types for time recording (replication from S/4 to FSM) Planning Board Customized | Service Notice Conversion to service Order Service Order Categorization Split of Responsability (User Status, Planner Group Dispatching Board Planning Scenario | Area Manager
Management of assets | Example of MCR Compain with dataset | MCR process | One sample smartform for replacement | Process of MCR Management, Service notification --> service order --> change of characteristics in S/4 | Area manager |  | smartform for service notice creation from FSM with required fields (ie material, ….)
Sprint 3
Management of assets |  | Retrofit process (revision) | revision type customized Smartforms ? Same than MCR or Identification ? Others ? | Revision creation, selection of equipments and creation of service orders | Method
Management of Assets | Specifications validated and delivred | Complete solution with custom developments |  |  | Method
Maintenance of Maintenance Plans | Specifications validated and delivred | Complete solution with custom developments |  |  | Method
Sprint 4
Process 4 : Planning of Service Order |  | Long Term, Mid term & Short term planning for all processes | Teams and Crews created for some Work Centers | Service Order Spare Parts reservation / PR Service Order corrective Maintenance generation Service Order Preventive Maintenance Verificiation and Release Dispatching and planning in FSM | Area Manager |  | Writing of development specifications Delivery of custom developments
Process 6 : Management of Safety and Compliance |  | Authorization / LOTO / JIV |  | Authorizations management in SAP FSM LOTO/JIV Smartform | Area Manager
Management of Service Order |  | Execution of Service order (spare part process, time recording, workflows, smartforms fullfilement, report generation) |  | Execution of Service order for main processes (preventive, corrective, MCR, retrofit, ..) | Technician
Management of Service Notice |  | Complete Solution with Custom Developments |  | Process creation of Service Notice from FSM with all required fields | Technician
Management of Service Order |  | Validation and closure |  | Time validation, service order verification and closure | Area manager |  | Writing of development specifications Delivery of custom developments
Sprint 5
backlog
Management of Subcontracting | Use Case : Subcontracting intervention | Subcontracting Onboarding and Execution | Crowd Workforce Customized in FSM | Use Case of Subcontracting Service Order Execution for Corrective Maintenance | Area Manager